## ReadMe
This design review checklist is designed to be used either as the checklist of a guidebook for the checklist.
Each question has assoicated help information embedded in a comment associated with that question. When printing you can either include a print of those comments or print without those comments. The template includes printing of those comments.
How to remove comment printing - to print just the checklist
File -> Page Setup
Sheet tab
Print options (middle of window) Comment pulldown select "(None)"
How to add comment printing - to print as a guidebook
File -> Page Setup
Sheet tab
Print options (middle of window) Comment pulldown select "At end of sheet"

## CheckList
Design Review - Software Identification
Software Component Name | PrmDb
Component Developer | Tim Canham
Component Peer Reviewers | Day, Wilf, Bocchino, Watney, Reder, Dinkel, Canham
Software Type | Reuse - No code changes allowed
Review Date | 6/25/2015, 198-102
Question Number | Subject | Developer Assessment | Peer Assessment | Comments
Requirements Phase Completion
1 | Are the component requirements complete, clear and unambiguous? | Yes | Yes | Specified in SDD
2 | Have the component requirements been associated with parent requirements? | N/A | N/A
3 | Have initialization requirements been specified? | N/A | N/A | Constructor arguments discussed in the SDD
4 | Have exception handling requirements been specified? | N/A | N/A | No exceptions allowed
5 | Have performance requirements been specified? | N/A | N/A
6 | Have the component requirements been identified with a verification method (Test, Demonstration, Inspection, Analysis) | Yes | Yes
7 | Are the component requirements documented in the SDF? | Yes | Yes
Design Phase Documentation
8 | Is there a documented high level statement for this component? | Yes | Yes | In the SDD
9 | Is there a MagicDraw Component model that captures the component specification with port interfaces? | Yes | Yes
10 | Has the component/port ISF XML specification been generated using the MagicDraw component plugin? | Yes | Yes | Manual used; autocoded in Autoxml
11 | Has the component model's IBD (Interface Block Diagram) been documented in the SDF? | Yes | Yes
12 | Have the component's commands been specified in an ISF XML command file? | Yes | Yes
13 | Have the component's telemetry been specified in an ISF XML telemetry file? | N/A | N/A
14 | Have the component's EVR's been specified in an ISF XML EVR file? | Yes | Yes
15 | Have the component's parameters been specified in an ISF XML Parameter file? | N/A | N/A
16 | Have assumptions with external (to the component) interfaces been described? | N/A | N/A
17 | Are all the component design artifacts documented in the SDF? | Yes | Yes
Design Content
18 | Have the states of the component been defined and specified? | N/A | N/A
19 | Have the components internal architecture been defined? | Yes | Yes
20 | Have the algorithms to be implemented been identified? | Yes | Yes | Method of divding described in SDD
21 | Have the use-cases been defined? | Yes | Yes
22 | Have the component port types been defined? | Yes | Yes
23 | Have critical areas been identified, documented and protected? | Yes | Yes
24 | Has logic been defined for each function/method? (PDL, Sequence Diag) | Yes | Yes | Sequence Diagrams in SDD
25 | Have global data items been defined? | N/A | N/A
26 | Have data items been properly initialized? | N/A | N/A
27 | Does the design satisfy the component requirements? | Yes | N/A
Summary
28 | Have all the action items been captured from this design peer review? |  | Yes
29 | Is the design ready to progress to the code phase? |  | Yes
Process Improvement
30 | Were all checklist items (questions and / or comments) clear? | Yes | Yes
31 | Was the checklist complete? |  | Yes
Note on A3: Module Developer The name of the engineer responsible for developing this module.
Note on A4: Component Peer Reviewers All the reviewers for this component
Note on A5: Software Type Use pulldown option: Reuse - No code logic changes allowed Re-engineer - Code changes planned (<20%) New - > 20% modified or no heritage basis
Note on A6: Review Date The date the requirements review is held.
Note on C8: Developer Assessment To be completed by the developer prior to the walkthrough. All software has the developer perform the initial assessment here.
Note on D8: Peer Assessment To be completed by the peer during the walkthrough assessment.
Note on B10: There should be sufficient requirements levied on this component to enable the developer to adequately perform the implementation of the component. Requirements should be testable, clear and unambiguous
Note on B11: The component requirements should be mapped to higher requirements such as Flight Software requirements.
Note on B12: If there is any special initialization it should be identified in the requirements. If no initialization requirements are appropriate then answer N/A and specify there are none in the comments.
Note on B13: If there is any exception handling it should be identified in the requirements. If not then answer N/A and specify
Note on B14: Any performance specification that pertains to the development of this component. It would not be appropriate to specify requirements on how the component may be used on a system. Ie different implementations and users of this component may assign priorities during instantiation but that information is not enbedded in the component and thus performance requirements of that nature would not be levied on the component.
Note on B15: Some requirements may be verified at a higher level ie at the fsw requirement level not at the component requirement level.
Note on B16: Either in the software development folder, wiki, or in a separate Software Requirements document.
Note on B18: The high-level statement of the component should provide a good overview of what the component needs to do. It should serve as an introduction to the component.
Note on B19: If the project is using a model to specify the software components and connections then check that this component is modeled and the Plugin is used to automatically generate the ISF XML component and port specifications. The MagicDraw ISF Profile provides the ISF component and port types necessary to specify the model for automatic code generation. If the project chooses not to model then answer N/A
Note on B20: If the project is developing a component model, then the MagicDraw component plugin should be used to generate the ISF XML specification. Check that the model is correctly specified by running the plugin to generate the XML.
Note on B21: If using a model then the MagicDraw component IBD should be captured in the SDF.
Note on B22: These are ground-based or operator commands that will need to be implemented. They are part of the application's command dictionary.
Note on B23: These are the ground based telemetry channels contained within this component and form part of the application's telemetry dictionary.
Note on B25: Configuration parameters for this component that are typically loaded and saved in NVM but are dependent on the mission behavior.
Note on B26: If there are assumptions about interfaces with anything outside of the component are being made, what are they? Are they documented in the SDF? If no assumptions are being made, then indicate this is N/A and include that in the comment.
Note on B29: A formal component state-machine diagram is desirable especially if the state behavior is non trivial. A formal state-machine model in MagicDraw can be auto-generated.
Note on B30: Typically captured in a class diagram for class relationships such as inheritance and composition. If the architecture is trivial then answer with N/A .
Note on B31: Specify what if any algorithms this component has to implement - ie estimator filtering, sorting, searching.
Note on B32: Describe some typical use-cases in which this component will be used. This could be captured in a sequence diagram for non trivial cases.
Note on B33: The component's port type data structures should be fleshed-in at this time. This includes definitions down to primitive data types and any returns, pass by value, pointer, reference etc.
Note on B34: Special areas to scrutinize are syncrhonous non guarded input ports that may be used by multiple tasks
Note on B35: The logic for each function/method should be defined. Various ways to define this logic are available. The use of a Pseudo Design Language (PDL) is one way. The use of a UML Sequence Diagram is another way. There should be enough information here to enable a developer to start writing and testing code.
Note on B36: All global data items should be defined. If there are no global data items that are needed to implement the design then a response of N/A with a note that there are none in the Comments field is appropriate.
Note on B37: All data items should be initialized before use. Have design features been included showing that this has been done.
Note on B41: Don’t answer until all other questions are complete. This is the collective view of the reviewers within the peer review.
Note on B43: If any items are not clear or need to be reworked identify what the issue is.
Note on B44: If any items came up that were not associated with a checklist item, but should be looked at systematically in future reviews, identify what that item is so it can be added to the checklist.

## Criteria
Yes/No | Software Development Type Definitions | Software Catetory Definitions
Yes | Reuse - No code changes allowed | 1 - Mission/Safety Critical
No | Re-engineer - Code changes planned | 2 - Mission/Safety Critical Support
N/A | New - new or >20% modified | 3 - Non-Mission/Safety Critical Support
4 - Engineering Support